## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 70 | 63
1 | 58 | 63
2 | 26
3 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 26 | 26
19 |  | 26 | Week 6 Monday
18 |  | 24
17 |  | 22
16 |  | 22
15 | 20 | 22
14 |  | 20 | Week 7 Monday
13 |  | 20
12 |  | 14
11 |  | 8
10 | 15 | 8
9 |  | 8 | Week 8 Monday
8 |  | 8
7 |  | 8
6 |  | 6
5 | 10 | 6
4 |  | 6 | Week 9 Monday
3 |  | 6
2 |  | 6
1 |  | 6
0 | 0 | 6
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20
19 |  |  | Week Monday
18
17
16
15
14 |  |  | Week Monday
13
12
11
10
9 |  |  | Week Monday
8
7
6
5
4 |  |  | Week Monday
3
2
1
0 | 0