## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 70 | 70
1 | 58 | 63
2 | 26 | 26
3 | 0 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 26 | 26
19 |  | 26 | Week 6 Monday
18 |  | 24
17 |  | 22
16 |  | 22
15 | 20 | 22
14 |  | 20 | Week 7 Monday
13 |  | 20
12 |  | 14
11 |  | 8
10 | 15 | 8
9 |  | 8 | Week 8 Monday
8 |  | 8
7 |  | 8
6 |  | 6
5 | 10 | 6
4 |  | 6 | Week 9 Monday
3 |  | 6
2 |  | 6
1 |  | 6
0 | 0 | 6
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 31 | 31
19 |  | 34 | Week 10 Monday
18 |  | 34
17 |  | 33
16 |  | 32
15 | 20 | 30
14 |  | 30 | Week 11 Monday
13 |  | 27
12 |  | 22
11 |  | 20
10 | 10 | 20
9 |  | 19 | Week 12 Monday
8 |  | 14
7 |  | 14
6 |  | 6
5 | 5 | 6
4 |  | 2 | Week 13 Monday
3 |  | 2
2 |  | 2
1 |  | 0
0 | 0 | 0